## Overview
| 2011 | 2012 | 2013 | 2014 | 2015
Standard GAS Filter
Pre-Isolator Mechanics
Pre-Isolator Controls
Payload
Type-B Full

## Coarse Plan
|  |  |  | 2013 |  |  | 2014
|  | Person | Site | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Moving | Moving Preisolator | ryu, seki | K->NAOJ
Filter 1 | Standard filter magic wand tuning | ono,seki | ICRR
Frame | Outer Frame modal analysis | Lundock | 20m
OSEM | OSEM test & calibration | fab,seki | 20m
Payload | Payload prototype test | seki | 20m
Op Lev | Optical lever setup & test | aga,seki | TAMA
Vacuum | Vacuum test | ryu | TAMA
Preisolator | Preisolator mechanical setup |  | TAMA
| Control test in vacuum |  | TAMA
Fixed Pay | Installation, cabling |  | TAMA
| Torsion damping test |  | TAMA
Full Test | Release payload |  | TAMA
| Full system test |  | TAMA

## Plan Management
[5 empty] | 2013 | [5 empty] | 2014
|  | Status | Person | Site | Oct |  | Nov |  | Dec |  | Jan |  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Moving | Moving Preisolator | DELAYED | ryu, seki | to TAMA |  |  |  | A
| Packing preiolator | 10/15 finished | ryu, seki, koni | ICRR
| Packing IP base and pistons | 10/15 finished | ryu, seki, koni | ICRR
| Packing small items | 10/16 Planned, BUT DELAYED in 10/22 | ryu, seki | ICRR
| Packing digital system | on 10/30 finished | seki, miya,istk | ICRR
| Sending digital system | on 10/31 finished | seki,kami | ICRR |  |  | E
| Sending pistons, rack, bellows | on 11/8 | tok,seki | ICRR
| Sensing preisolator, top chamber | on 11/13 | ryu,fab | TAMA
| Bottom Filter Deliver | 10/8 fninished | ryu | to 20m
| Removing TAMA-SAS at West End | Finished??? | ryu, fab | TAMA
| Cleaning 20m laboratory | Planned 11/5-8 | fab,joris,aga | 20m
| Moving Standard Filter and damper |  | ryu, seki, ono | TAMA
| Assemble hat for moving |  | seki,ono | ICRR
| Disassemble LVDT, actuators and so on |  | seki,ono | ICRR
| Moving by a car |  | ryu | to NAOJ
ICRR | Standard filter magic wand tuning |  | ono,seki | ICRR
| Designing frames and jigs to put actuators | 10/17 finished | ono,seki | ICRR
| Ordering frames and jigs | Ordered. Will be deliverred on ??? | ryu | ICRR
| Deliverring coil drivers from NAOJ | 10/11 finished | ryu | ICRR
| Checking performance of the driver | 10/16 finished | ono, seki | ICRR
| Outside the frame, measurement test with act & pzt | Planned 10/18-22, 10/28 finished | ono, seki | ICRR
| Coarse accelerometer calibration | Tried on 10/28, acc doesn't work | ono | ICRR
| Acquire reliable accelerometers |  | ono,seki,ryu | ICRR
| Assembly frames | Planned 10/28-30 | ono, seki | ICRR
| Transfer function measurement |  | ono | ICRR
| Noise hunting, peak investigation (hammering test) |  | ono | ICRR
| Tuning of magic wands |  | ryu, ono | ICRR
| Torsion mode damping test | (If measurement of TF finishes in Nov...) | ono,seki | ICRR
| Desiging frames for suspending SF & MD |  | ono,seki | ICRR
| Ordering frames and jigs |  | ryu | ICRR
| Checking wires to suspend SF & MD | MD wires checked. Length check is not yet | ryu,seki | ICRR
| Considering torsion mode sensor on the payload | Photo sensor (Sharp) may be useful | ryu,seki,ono | ICRR
| Performance test of coarse displacement sensor |  | ono | ICRR
| Suspending SF & payload |  | ono,seki | ICRR
| Calculating MoI and expected frequency |  | ono | ICRR
| Preparation of sensors |  | ono,seki | ICRR
| Measurement without damper |  | ono | ICRR
| Putting magnets on the damper |  | ono,seki | ICRR
| Suspending MD |  | ono,seki | ICRR
| Measurement of damping efficiency |  | ono | ICRR
| Tuning of damping coefficient with magnets |  | ono | ICRR
Frame | Outer Frame modal analysis | DELAYED due to delay in delivery | rums | TAMA
| Learing measurement system |  | rums | TAMA
| Measurement without load |  | rums | TAMA
| Measurement with load | DELAYED | rums | TAMA |  |  |  | A
| Outer Frame seismic noise measurement | DELAYED due to delay in delivery | rums | TAMA | [5 empty] | B
OSEM | OSEM Nick's circuit prototype test |  | fab | 20m
| Ordering items | 10/4 finished | fab,ryu | 20m
| Assembling items | 10/20 finished | fab | 20m
| Operation check | set as lower priority | fab | 20m
| Noise measurement | set as lower priority | fab, joris | 20m
| Calibration | set as lower priority | fab, joris | 20m
| OSEM temporary circuit test |  | ryu,fab | 20m
| Design circuits | Finished on 10/22, Ryu will send circuit. | ryu | 20m
| Fabricate 1 circuit | Finished on 10/24 | fab | 20m
| Calibration test (test circuit) | on going | fab | 20m |  | D
| Noise measurement (test circuit) | on going | fab | 20m
| Ordering circuit / fabricate 10 circuits |  | ryu,fab | 20m
| Noise measurement |  | fab | 20m
| Calibration |  | joris,fab | 20m |  |  | D
| OSEM calibration bench setup | ongoing | fab | 20m |  | D
Payload | Assembly of Payload |  | ryu,fab,seki,joris | 20m
| Assembling OSEMs on TM |  | fab,joris | 20m
| Assembling recoil mass |  | fab,joris | 20m
| Assembling OSEMSs on IM |  | fab,joris | 20m
| Assembling intermediate stage |  | fab,joris | 20m
| Assembling bottom filter |  | fab,joris | 20m
| Tuning of IM pitch frequency |  | seki,joris | 20m
| Preparation of measurement system |  | ryu,seki | 20 m
| Preparing LVDT and VoCo drivers |  | ryu,seki | 20m
| Preparing motor drivers |  | ryu,seki | 20m
| Preparing standalone digital system |  | seki | 20m |  |  | E
| Operation check |  | fab,seki,joris | 20m
| Bottom filter operation check |  | seki,joris | 20m
| Picomotor (torsion) test |  | ryu,joris | 20m
| Picomotor (IM balance) test |  | ryu,joris | 20m
| Mechanical TF measurement |  | fab,seki,joris | 20m
| Mechanical TF from act to sens |  | joris,fab | 20m
| Diagonalization, separate to each DoF |  | fab | 20m
| Comarison with Simulated TFs |  | seki | 20m
| Payload control test |  | fab,seki | 20m | [7 empty] | C
| Designing control filters |  | fab,seki | 20m
| Constructing filters on digital system |  | seki | 20m
| Applying control, instability check |  | fab,seki | 20m
| Measurement of OLTF, CLTF |  | fab,seki | 20m
| Long term operation test |  | fab | 20m
Op Lev | Pylon preparation |  | ryu,akt,seki,aga | ICRR
| Deciding rough layout | Finished. Light goes throuhg beam duct. | ryu,seki | ICRR
| Making base requirement for pylon design | until 10/24 | seki,aga,akt | ICRR
| Making specific requirement optical lever | until 11/1 | seki | ICRR
| Discussion of the way of anchering pylon on floor | TBC | akt,saito | NAOJ
| Discussion with ATC for pylon design&production |  | seki,akt | NAOJ
| Designing pylon and FEM analysis |  | ATC,seki,akt | NAOJ
| Pylon production |  | ATC | NAOJ
| Driver circuit for PSD |  | akt,seki,miya | ICRR
| Checking LIGO circuit |  | akt | NAOJ
| Noise budget of electronics & optics |  | seki | ICRR
| Designing drive circuit |  | akt,miya | ICRR
| Discussion about production & packing |  | miya,kami,akt | ICRR
| Production for prototype test in TAMA |  | miya,kami | ICRR
| Optical lever test on optical bench |  | aga,seki | 20m
| Measurment on viewport random surface | closed?? | akt | NAOJ
| Bollowing SLD from viewport measurement |  | aga | 20m
| Resetup for drift & noise measurement |  | aga,seki | 20m
| Drift measurement with current model |  | aga | 20m
| Drift measurement with fixed lens |  | aga | 20m
| Drift measurement without starring mirror |  | aga | 20m
| Optical lever test with pylon |  | aga,seki | TAMA
| Preparation of the floor |  | ATC | TAMA
| Installation of pylon |  | aga,seki,majo | TAMA
| Measurement of mechanical resonances of pylon |  | seki,majo | TAMA
| Installation and setup of optics on pylon |  | seki | TAMA
| Drift measurement with pylon |  | seki | TAMA
| Optical lever test on TAMA |  | seki | TAMA
| Arrangement of optical layout |  | seki | TAMA
| Placing optics in vacuum chamber |  | seki | TAMA
| Vacuum the tank |  | seki
| Drift and noise measurement |  | seki
Vacuum | Vacuum test |  | ryu | TAMA | [5 empty] | B
Preisolator | Preisolator mechanical setup |  | seki | TAMA
| Digital system re-setup |  | seki | TAMA | [7 empty] | C
| Preisolator control test in vacuum |  | seki,fab,ono? | TAMA
Almost-Full | Installation, cabling |  |  | TAMA
(Fixed pay) | Torsion damping with fixed payload |  |  | TAMA
| Pre-isolator control test |  |  | TAMA
| Optical lever working test |  |  | TAMA
| Length sensor (TBD) setup |  |  | TAMA
Full Test | Release payload |  |  | TAMA
| picomotor working check |  |  | TAMA
| OSEM working check |  |  | TAMA
| Mechanical TF measurement |  |  | TAMA
| Full control test |  |  | TAMA
| Long term observation |  |  | TAMA

## Tips
AI
Another frame for Bottom Filter Test
LVDT driver or other sensors for Bottom Filter
Payload for PI
Light source for oplev | OK
coil drivers | TO BE TESTED
PSD driver??? | commercial one / home made