Main Interferometer Subsystem
Installation and Commissioning Plans
Yoichi Aso
KAGRA F2F Meeting
2014/2/13

---
What have we done so far ?
Optical Design
Signal Extraction Scheme
Optical Layout
Mirror specs.
Noise requirements
Y-arm
ITMY
PRM
REFL
PR2
POX
ITMX
ETMX
Laser Beam
From MC
BS
X-arm
PR3
SR2
AS_DC
OMC
SR3
SRM

---
Things to be prepared before the installation begins
(for iKAGRA)
  For Control
Detailed servo design
Analog Circuits
(RFPD, DCPD, RFQPD, DCQPD, Demodulator, Whitening Filter,
RF Distribution, CARM servo board, MC servo board)
Realtime code
For light detection
Optical layout for detection benches
Beam Shutters (?)
Optical tables for detection benches (IOO)
Miscellaneous small optics
(mirrors, holders, lenses, polarizers, etc) (IOO)

---
Installation
Electronics
Installation into racks
Cabling
all by done by ourselves

---
Installation
Detection Bench
Put optical tables when the space is possible
Roughly put PDs on the table and start wiring
Assemble detection optics when the light comes
out of the chamber

---
Installation
Mirrors
How to put mirrors at precise locations (esp. PRC, SRC)
Interferometric verification of distances ?
Initial alignment procedure
Mode matching confirmation

---
Commissioning
Interferometer commissioning can start only after the BS installation
Michelson -> X-arm -> Y-arm -> FPMI
in 5 months !?
2 - 3 MIF commissioning people at the site
At least 1 MIF expert
At least 1 suspension expert, 1 RTS expert must be present

---
What about bKAGRA ?
Put important PDs into vacuum
Air-tight enclosures
Vacuum compatible beam shutters
Output optics
Output Faraday
Output Mode Matching Telescope
Output Mode Cleaner
Green Lock System