Main Interferometer Subsystem
What to do with iKAGRA
Yoichi Aso
2014/4/16

---
ETMY
Mode Cleaner
Vacuum
ITMY
PRM
PR2
ITMX
ETMX
BS
PR3
SR2
Laser Bench
SR3
SRM
bKAGRA
GW Signal
OMC

---
ETMY
Mode Cleaner
ITMY
Vacuum
PR2
ITMX
ETMX
BS
PR3
Laser Bench
iKAGRA

---
Important differences between iKAGRA and bKAGRA
DRFPMI -> FPMI
IMMT will not be optimized for iKAGRA (poor mode matching)
No green lock
POX is available but POY separation may be difficult
No WFS for the main interferometer

---
Commissioning
Interferometer commissioning can start only after the BS installation
Michelson -> X-arm -> Y-arm -> FPMI
in 5 months !?
2 - 3 MIF commissioning people at the site
At least 1 MIF expert
At least 1 suspension expert, 1 RTS expert must be present

---
More detailed schedule
BS installed
Year 2015
1	2	3	4	5	6	7	8	9	10	11	12
MC initial lock
MC commissioning
IMMT installation
PRC Mode check
MICH
X-arm
Y-arm
FPMI lock
Observation

---
More detailed schedule
Year 2015
7	8	9	10	11	12
MICH
Initial alignment
Check PDH
Close loop
Optimize servo
X-arm
Y-arm
Initial alignment
Check PDH
Close loop
Optimize servo
Initial alignment
Check PDH
Close loop
Optimize servo
FPMI lock
Observation
Align two cavities
Lock two cavities independently
at the same time
Lock MICH
Hand off to DARM CARM
Lock CARM with the laser

---
bKAGRA Schedule
PRMI(Sapphire mirror)
DRMI(Sapphire)
	2016					2017
12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12
DRMI
ITM Installation
Independent
Arm lock
Use silica ITMs
Same signal
extraction scheme
DRFPMI
Sapphire mirrors
But room temperature
Cryogenic

---
No DRMI
ETMY
ITMY
PRM
PR2
ITMX
ETMX
BS
PR3
SR2
SR3
SRM

---
No DRMI
ETMY
ITMY
PRM
PR2
ITMX
ETMX
BS
PR3
SR2
SR3
SRM

---
No DRMI
ETMY
ROCs are wrong !
13.6km
instead of 1.9km
ITMY
PRM
PR2
ITMX
ETMX
BS
PR3
SR2
SR3
SRM

---
bKAGRA Schedule
PRMI(Sapphire mirror)
DRMI(Sapphire)
	2016					2017
12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12
DRMI
ITM Installation
Independent
Arm lock
Use silica ITMs
Same signal
extraction scheme
DRFPMI
Sapphire mirrors
But room temperature
Cryogenic

---
bKAGRA Schedule
PRMI(Sapphire mirror)
DRMI(Sapphire)
	2016					2017
12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12
iKAGRA
ITM Installation
Independent
Arm lock
Do more commissioning
Integration with bKAGRA Input
Optics
Test output optics ?
More tests useful for bKAGRA ?
(Under discussion)
DRFPMI
Sapphire mirrors
But room temperature
Cryogenic

---
Stable PRC ?
ETMY
Additional Lens
ITMY
PRM
PR2
ITMX
ETMX
BS
PR3
SR2
SR3
SRM

---
What can we learn from iKAGRA ?
Common elements
Tunnel, Facilities, Vacuum (?)
MC, Faraday(?), IMMT(?), PR2, PR3, BS
Some analog circuits
Digital System
Possible tests/measurements
MC commissioning/characterization
WFS
Beam jitter after MC
RF AM (RFSB transmission servo)
Type-B controllability check
Scattered light estimation
Building noise budget system
Seismic feed forward test

---
Suggestions from Rana
1) Common mode servo for frequency stabilization.
2) Measurements of loss/scattering in the arms
(not important for bKAGRA, but useful technique to develop)
3) Comparison of ground motion with relative interferometric motions
4) Use MICH as an out-of-loop sensor for the DARM DOF.
Excess sensing noise of the differential arms or individual arm noises.
5) Auto Noise Budget for FPMI.
6) RF chain noise and distortion.

---
7) Budgeting of low frequency suspension angular motion using
optical levers and dither readout.
8) Mode matching diagnostic by slow arm cavity mode scan.
9) Use GIF to do Wiener seismic FF for CARM/DARM.
10) Measure delay and packet CRC for digital loops.
Loopback fidelity tests of RFM. Digital filter noise generation.
11) Schnupp asymmetry measurement as diagnostic of
initial optic placement.
12) Compare FPMI contrast with FFT models.
13) Use simple green laser generation and beat frequency detection
for ALS prototyping.