## Slide 1: Project/SEO report
1. Present status of iKAGRA
  ** Master schedule and delay of iKAGRA
  ** iKAGRA configuration (Michelson Interferometer) and Beam Splitter
  ** installation so far done
2. Scheduling of iKAGRA installation/commissioning
  ** milestone
3. bKAGRA (2016-17)
  ** Task force for updating “budget schedule and roadmap of bKAGRA”
151215_SAITO

## Slide 2: KAGRA Master Schedule
bKAGRA
iKAGRA
・iKAGRA (2010.10 – 2015.12)
3-km FPM interferometer
- Baseline 3km room temp.
- Operation of total system
with simplified IFO and VIS.
2012
2013
2014
2015
2016
2017
OBS
2018
・bKAGRA (2016.1 – 2018.3)
Operation with full config.
- Final IFO+VIS configuration
- Cryogenic operation.
Cryo-mirrors
Recycling
mirrors
150709_SAITO

## Slide 3: KAGRA Master Schedule
bKAGRA
iKAGRA
・iKAGRA (2010.10 – 2016.3)
3-km FPM interferometer
- Baseline 3km room temp.
- Operation of total system
with simplified IFO and VIS.
2012
2013
2014
2015
2016
2017
OBS
2018
・bKAGRA (2016.1 – 2018.3)
Operation with full config.
- Final IFO+VIS configuration
- Cryogenic operation.
Cryo-mirrors
Recycling
mirrors
151215_SAITO
iKAGRA delayed

## Slide 4: Project/SEO report
1. Present status of iKAGRA
  ** Master schedule and delay of iKAGRA
  ** iKAGRA configuration (Michelson Interferometer) and Beam Splitter
  ** installation so far done
2. Scheduling of iKAGRA installation/commissioning
  ** milestone
3. bKAGRA (2016-17)
  ** Task force for updating “budget schedule and roadmap of bKAGRA”
151215_SAITO

## Slide 5: iKAGRA configuration (Michelson Interferometer)
150709_SAITO
IO
MC
Cryogenic system test
- Cryostat + Rad. shield duct
- Cryo-cooler
- Cryogenic payload
- Fixed Type-A SAS
ETM
Y-arm
X-arm
ETM
BS
Type-A isolator
full-system test
- Room-temp. test
Sapphire (?), 23kg, 290K
- Tall seismic isolator
IP + GASF + Payload
Shorter arm
length by 61m
iKAGRA configuration
- Room-temp. test masses
suspended by Type-Bp payload
- MI with 2.94 km arm
- Low laser power, w/o power recycling
- On-site test of VIS and Cryo system
iKAGRA obs. Run in Dec. 2015 ~1 month
Type-C system
- Mode cleaner
Silica, 0.5kg, 290K
- Stack + Payload
Type-Bp payload;
Test mass and core optics.
Table + GASF + Type-B payload.
Type-B payload;
Beam splitter
IP + GASF + payload

## Slide 6: iKAGRA configuration (Michelson Interferometer)
151215_SAITO
IO
MC
Cryogenic system test
- Cryostat + Rad. shield duct
- Cryo-cooler
- Cryogenic payload
- Fixed Type-A SAS
ETM
Y-arm
X-arm
ETM
BS
Type-A isolator
full-system test
- Room-temp. test
Sapphire (?), 23kg, 290K
- Tall seismic isolator
IP + GASF + Payload
Shorter arm
length by 61m
iKAGRA configuration
- Room-temp. test masses
suspended by Type-Bp payload
- MI with 2.94 km arm
- Low laser power, w/o power recycling
- On-site test of VIS and Cryo system
iKAGRA obs. Run in Mar. 2016 ~1 month
Type-C system
- Mode cleaner
Silica, 0.5kg, 290K
- Stack + Payload
Type-Bp payload;
Test mass and core optics.
Table + GASF (simplified) + Type-B payload.
Type-B payload;
Beam splitter
IP + GASF + payload Type-C (to use CLIO BS mirror/suspension)
Further changed in iKAGRA

## Slide 7: iKAGRA configuration (Michelson Interferometer)
151215_SAITO
IO
MC
Cryogenic system test
- Cryostat + Rad. shield duct
- Cryo-cooler
- Cryogenic payload
- Fixed Type-A SAS
ETM
Y-arm
X-arm
ETM
BS
Type-A isolator
full-system test
- Room-temp. test
Sapphire (?), 23kg, 290K
- Tall seismic isolator
IP + GASF + Payload
Shorter arm
length by 61m
iKAGRA configuration
- Room-temp. test masses
suspended by Type-Bp payload
- MI with 2.94 km arm
- Low laser power, w/o power recycling
- On-site test of VIS and Cryo system
iKAGRA obs. Run in Mar. 2016 ~1 month
Type-C system
- Mode cleaner
Silica, 0.5kg, 290K
- Stack + Payload
Type-Bp payload;
Test mass and core optics.
Table + GASF (simplified) + Type-B payload.
Type-B payload;
Beam splitter
IP + GASF + payload Type-C (to use CLIO BS mirror/suspension)
Further changed in iKAGRA

## Slide 8: iKAGRA configuration (Michelson Interferometer)
151215_SAITO
IO
MC
Cryogenic system test
- Cryostat + Rad. shield duct
- Cryo-cooler
- Cryogenic payload
- Fixed Type-A SAS
ETM
Y-arm
X-arm
ETM
BS
Type-A isolator
full-system test
- Room-temp. test
Sapphire (?), 23kg, 290K
- Tall seismic isolator
IP + GASF + Payload
Shorter arm
length by 61m
iKAGRA configuration
- Room-temp. test masses
suspended by Type-Bp payload
- MI with 2.94 km arm
- Low laser power, w/o power recycling
- On-site test of VIS and Cryo system
iKAGRA obs. Run in Mar. 2016 ~1 month
Type-C system
- Mode cleaner
Silica, 0.5kg, 290K
- Stack + Payload
Type-Bp payload;
Test mass and core optics.
Table + GASF (simplified) + Type-B payload.
Type-B payload;
Beam splitter
IP + GASF + payload Type-C (to use CLIO BS mirror/suspension)
Further changed in iKAGRA
KAGRA BS
Diameter: 200 mm
Thickness: 80 mm
HR point (injection point) of CLIO BS
is to be adjusted as the same position
as of KAGRA.
The thickness difference does not cause
any large shift at the ETM.

## Slide 9: Project/SEO report
1. Present status of iKAGRA
  ** Master schedule and delay of iKAGRA
  ** iKAGRA configuration (Michelson Interferometer) and Beam Splitter
  ** installation so far done
2. Scheduling of iKAGRA installation/commissioning
  ** milestone
3. bKAGRA (2016-17)
  ** Task force for updating “budget schedule and roadmap of bKAGRA”
151215_SAITO

## Slide 10: iKAGRA installation so far done by Mar 2015
Clean booths constructed;
MC, PR, BS, EX(Y)C chambers.
Preparing for filter operation.
150709_SAITO
IO
MC
ETM
Y-arm
X-arm
ETM
BS
Four of cryo-chambers installed.
Chambers for IP carried up in 2nd floor.
Two of 3-km KAGRA arm tubes (800 mm in dia.)
and 125 of baffles jointed and leak-tested.
Two of 1.5-km GIF tubes (400 mm in dia.)
jointed and leak-tested.
All the vacuum chambers aligned and anchored
EXC
PR
EYC
SR
Laser booth cleaned.
Optical bench set upped.
Preparing for input-optics setting.
Type-Bp payload;
Inner frames prepared.
Adding traverser under the first filter.
Type-C payload;
Base plate and stacks set upped.
Preparing to set breadboard.
Type-B payload;
Outer frame set upped and anchored.
The prototype tested in TAMA.
Control system installed in the computer room inside tunnel.
Network between tunnel and Mozumi office connected.

## Slide 11: iKAGRA installation (from Apr to Dec 2015)
151215_SAITO
IO
MC
ETM
Y-arm
X-arm
ETM
BS
EXC
PR
EYC
SR
MC mirrors and FI installed on Type-C VIS.
Clean booths for iKAGRA TMs constructed.
Inside the booths of PR, BS area re-cleaned,
being kept as Class-4, or better.
Beam injected in one of the 1.5-km GIF arms.
Two of 3-km KAGRA arm being kept in vacuum.
Full assy, but with a spare mirror, of PR3 is being installed.
Support structure of CLIO BS on the KAGRA optical bench prepared.
MC
BS
PR
Racks for local controller/driver distributed close to the booths, and linked to the network

## Slide 12: Project/SEO report
1. Present status of iKAGRA
  ** Master schedule and delay of iKAGRA
  ** iKAGRA configuration (Michelson Interferometer) and Beam Splitter
  ** installation so far done
2. Scheduling of iKAGRA installation/commissioning
  ** milestone
3. bKAGRA (2016-17)
  ** Task force for updating “budget schedule and roadmap of bKAGRA”
151215_SAITO

## Slide 13: iKAGRA commissioning milestone in 2015
10/14; EXA (ETM-X) mirror suspended
11/4; EYA (ETM-Y) mirror suspended
7/30; optics of IFI and IMM installed
150709_SAITO
IO
MC
ETM
Y-arm
X-arm
ETM
BS
9/1 – 11/30; commissioning
11/30; Michelson lock
12/2 - ; iKAGRA observation
EXC
PR
EYC
SR
6/9; PSL beam quality check
11/3; BS mirror suspended
  8/24; PR3 mirror suspended
  9/17; PR2 mirror suspended
  8/17; MC lock
5/8; control system started working.
6/30; control room in Mozumi office ready for operation.

## Slide 14: iKAGRA commissioning milestone in 2015
3/18; EXA (ETM-X) mirror suspended
3/11; EYA (ETM-Y) mirror suspended
12/11; MC mirrors aligned,
and a transmission fringe from MC observed
151215_SAITO
IO
MC
ETM
Y-arm
X-arm
ETM
BS
3/22 - ; iKAGRA observation
EXC
PR
EYC
SR
6/9; PSL beam quality check
12/22; BS mirror (CLIO) suspended
  12/22; PR3 test hanging
  (full assy with a spare mirror)
  1/28; PR2 mirror suspended
  2/5; PR3 mirror suspended
VIS installation;
  6 weeks for each ETM
  7 weeks for each PR
by two teams for four mirrors

## Slide 15: iKAGRA commissioning milestone in 2015
3/18; EXA (ETM-X) mirror suspended
3/11; EYA (ETM-Y) mirror suspended
12/11; MC mirrors aligned,
and a transmission fringe from MC observed
151215_SAITO
IO
MC
ETM
Y-arm
X-arm
ETM
BS
3/22 - ; iKAGRA observation
EXC
PR
EYC
SR
6/9; PSL beam quality check
12/22; BS mirror (CLIO) suspended
  12/22; PR3 test hanging
  (full assy with a spare mirror)
  1/28; PR2 mirror suspended
  2/5; PR3 mirror suspended
VIS installation;
  6 weeks for each ETM
  7 weeks for each PR
by two teams for four mirrors

## Slide 16: iKAGRA commissioning milestone in 2015
3/18; EXA (ETM-X) mirror suspended
3/11; EYA (ETM-Y) mirror suspended
12/11; MC mirrors aligned,
and a transmission fringe from MC observed
151215_SAITO
IO
MC
ETM
Y-arm
X-arm
ETM
BS
3/22 - ; iKAGRA observation
EXC
PR
EYC
SR
6/9; PSL beam quality check
12/22; BS mirror (CLIO) suspended
  12/22; PR3 test hanging
  (full assy with a spare mirror)
  1/28; PR2 mirror suspended
  2/5; PR3 mirror suspended
iKAGRA delayed
VIS installation START SOON!!;
  6 weeks for each ETM
  7 weeks for each PR
by two teams for four mirrors.
Each team needs 1 more shift
(Total 2 shift member) until
completion of VIS installation.

## Slide 17: Project/SEO report
1. Present status of iKAGRA
  ** Master schedule and delay of iKAGRA
  ** iKAGRA configuration (Michelson Interferometer) and Beam Splitter
  ** installation so far done
2. Scheduling of iKAGRA installation/commissioning
  ** milestone
3. bKAGRA (2016-17)
  ** Task force for updating “budget schedule and roadmap of bKAGRA”
151215_SAITO

## Slide 18: bKAGRA configuration
150709_SAITO
IO
MC
Type-A system
- Cryogenic test mass
Sapphire, 23kg, 20K
- Tall seismic isolator
IP + GASF + Payload
Type-C system
- Mode cleaner
Silica, 0.5kg, 290K
- Stack + Payload
ETM
ITM
Y-arm
X-arm
ITM
ETM
BS
SRM
PRM
Type-B system
- Core optics (BS, SRM,…)
Silica, 10kg, 290K
- IP + GASF + Payload
bKAGRA configuration
- Cryogenic test masses
- 3 km arm cavities
- RSE with power recycling
first science run in FY2017
Type-Bp payload
Test mass and Core optics (BS, FM,..)
Silica, 10kg, 290K
- Seismic isolator
Table + GASF + Type-B Payload

## Slide 19: bKAGRA configuration
150709_SAITO
IO
MC
Type-A system
- Cryogenic test mass
Sapphire, 23kg, 20K
- Tall seismic isolator
IP + GASF + Payload
Type-C system
- Mode cleaner
Silica, 0.5kg, 290K
- Stack + Payload
ETM
ITM
Y-arm
X-arm
ITM
ETM
BS
SRM
PRM
Type-B system
- Core optics (BS, SRM,…)
Silica, 10kg, 290K
- IP + GASF + Payload
- Stack for aux. optics
bKAGRA configuration
- Cryogenic test masses
- 3 km arm cavities
- RSE with power recycling
first science run in FY2017
Type-Bp payload
Test mass and Core optics (BS, FM,..)
Silica, 10kg, 290K
- Seismic isolator
Table + GASF + Type-B Payload
We need detailed plan to maximize the feasibility and achievement.