## Slide 1: Cryogenics Subgroup Report
Feb. 22, 2016
KAGRA F2F meeting @Kashiwa
Takayuki TOMARU, KEK

## Slide 2
Preparation Status of Cryogenic Pendulum
Tomaru, Miyamoto, Hagiwara, Suzuki
2. Preparation Status of Sapphire Suspension
Yamamoto, Tanaka, Kumar, Craig
3. Sapphire Prototype Suspension & Assembly Jigs
Craig, Kumar
4. Cryostat
Kimura, Tomaru, Suzuki
5. Schedule

## Slide 3
1st Practical Cryogenic Payload is under fabrication in VIC Co.
• Marionette
2 Moving Mass
6 Actuators & Sensors
• Marionette Recoil Mass
• Intermediate Mass
6 Actuators & Sensors
4 Damping Coil for vertical springs
• Intermediate Recoil Mass
• Dummy Mirror (by KEK)
4 Actuators
• Mirror Recoil Mass
(low magnetism Stainless Steel)
Fabrication will be done at end of this Mar.
Marionette
Intermediate
Mass
Mirror
CAD sets:
We have already haven prototype payload which is not including Marionette recoil mass
and Intermediate recoil mass.
1. Preparation Status of Cryogenic Pendulum
3D CAD model

## Slide 4
Category | Items | 2015 | 2016
Mirror懸架部品 | 鏡アクチュエータコイル | 4個 | 16個
 | 懸架SUSワイアー | 10m | 50m
Mirror Recoil Mass |  | 1 | 3
IM部品 | 中間マス(IM)製作 | 1 | 3個
 | サファイア板バネのダンピング用コイル | 4個 | 16個
 | CuBeブレード | 4 | 0
 | OpLev用鏡、ホルダー | 1 | 4
IM リコイルマス 一式 | 中間リコイルマス(IMRM)製作 | 1台 | 3台
MT一式 | マリオネット(MT)製作 [1+4式] | 1 | 3台
 | MTローカルセンサー ・アクチュエータ | 8個 | 32個
 | MTのMoving Mass(MM)用モータ、ドライバ | 2個 | 8個
 | MTのMoving Mass （Cu） | 4 | 12個
 | Moving Mass用ボールネジ, ベアリング等 | 2 | 8
 | IM-プラットフォーム(PF)間 Ti6Al4V 吊ロッド | 2本 | 6本
MT リコイルマス 一式 | MTリコイルマス製作 | 1 | 4
組立ジグ | 鏡とRMの位置決め治具 | (支給) | 4個
 | 鏡とファイバー、ブレード位置決めジグ | 0 | 4
 | 懸架系ホルダー | 0 | 4個
電気系 | ケーブル束ね治具 | 2個 | 8個
 | IM部コネクタ | 3個 | 12個
 | 4芯ポリイミド被覆ケーブル(高真空用) [1700m] | 1巻 | 0
Category | Items | 2015 | 2016
その他 | 実験機器ラック | 4台 | 0
 | 簡易クリンブース(現場作業用) | 0 | 4台
 | 鏡を持つための治具 | 0 | 1台
 | 低温懸架をクライオスタットにインストールするための設備 | 0 | 1台
 | 部品保管用のデシケーター | 2台 | 0
 | CMM | 1 | 0
 | パネルラック | 1 | 
 | 温湿度計 | 1 | 0
 | 傾斜計 | 2 | 
 | ロードセル |  | 1
 | クリーンブース用ジャッキ | 4台 | 
Platform | 差動トランス | 1個 | 4個
 | アルミナ製スラストベアリング | 2個 | 4個
 | PF回転用ステッピングモータ | 1個 | 4個
 | PF用CuBe板バネ材料•加工 | 6枚 | 20枚
 | PF用CuBe板バネの曲げ治具、材料•加工 | 4個 | 0
 | フィシングロッド板バネ | 1個 | 4個
 | フィッシングロッド用モータ | 1個 | 4個
 | PFのMM用W合金錘 | 3個 | 12個
 | 懸架系マス表面の黒化処理 | 0 | 24部品
 | PF構造体製作 | 1個 | 4個
 | 常温BF-低温PF間のTi6Al4Vロッド | 1 | 6本
 | 常温防振部とのケーブル接続コネクター | 2個 | 8個
 | 低温懸架保護フレーム | 1台 | 4台
 | 低温懸架部品精密洗浄 | 0 | 1式
Procurement Schedule

## Slide 5
Done
• Mechanical design
• Prototype fabrication
• Resonant frequency measurement of prototype
• Test fabrication of 5N purity Al heat link
• Setup of cryostat for payload test in KEK
Still Testing
• Mechanical simulation (~50%)
• Test fabrication of 6N purity Al heat link (~80%)
• Local sensor developments at cryogenic temperature (~50%)
• Ball screw test at cryogenic temperature for moving mass (70%)
• Design of assembly jigs (50%)
Not Yet
• Control Electronics
• black coating w/o magnetism
• Design of installation jigs
• Optical Lever
• Platform design

## Slide 6
6
6
6
6
6
6
6
We think extra sapphire fibers are necessary (They could be broken).
2. Preparation Status of Sapphire Suspension
Procurement of parts of KAGRA sapphire suspension
(except for mirrors themselves)
Almost half numbers of sapphire parts were ordered in this fiscal year.
Final parts will be delivered by July 2016.
Delivery is on time.
Items | CAD No. | 2015 | 2016 | 2015 comments
サファイアブレード | KAGRA-Cryo-mec-051-03 | 8 | 8 | ２セット分
サファイアワッシャー | KAGRA-Cryo-mec-051-01 | 16 | 48 | 1セット分
サファイアロッド | KAGRA-Cryo-mec-14-01 | 24 |  | 2セット分+テスト用, 鏡上のマグネットベース
ネールヘッド付ファイバー |  |  |  | 
Investigation of delivered products
Geometrical shape of sapphire ears : OK (So far) by Kazuhiro Enami (KEK)
Flatness of bonding surface with mirror is in progress. by Akitoshi Ueda (NAOJ)

## Slide 7
Test by using one fiber prototype
Simpler prototype (easier assembly)
Short cooling time
Sapphire blade spring
6kg sapphire mass
(1/4 of KAGRA mirror)
Sapphire fiber
D. Chen, H. Tanaka
145.3mm
145.3mm
67.5mm
Heat load test is in progress.
Large temperature difference (about 10K) between blade spring
and its support was found.

## Slide 8
3. Sapphire prototype suspension & Assembly Jigs

## Slide 9: Sapphire prototype suspension
Assembly frame designed and built
Earthquake stops assembled
Intermediate mass, and blade spring clamps assembled
Next step: HCB bonding ears to test mass
Assembly of full suspension (including indium bonds in suspensions)

## Slide 10
BS
3 km
3 km
IXC
IYC
EXC
4. Cryostat
EYC
Last two duct shields will be delivered
at the end of Mar.
Four duct shields at both ends will be
installed soon after iKAGRA.
Then assembly of cryostats will be done
at the same time.
Preparation for performance test
of duct shiled

## Slide 11
We lost data beween Nov. and Dec. since PC trouble, but it didn’t change from above.
Re-alignment of the cryostats will be done at Mar.

## Slide 13
5. Schedule
 | 2016 |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  | 
 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
Cryo-Payload No.1 Fab. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Payload No. 1 Assembry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Pay. No. 1 test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Local Sensor Test & Impro. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Pay. Proto. improvement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Paylaod No. 2, 3, 4 Fab. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Paylaod No. 2, 3, 4 Assem. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Pau. No. 2-4 test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Heat Link Fab. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Platform Design & Fab. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Assembly Jig Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Indium Bonding Test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sapphire Fiber Fab. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sapphire Proto. Assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HCB to ETM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ETM sapphire assembly & test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HCB to ITM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ITM sapphire assembly & test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Assemble Sapphire to Pay. 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Assemble Sapphire to Pay. 2 - 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EXC cryostat assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EYC cryostat assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IXC cryostat assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IYC cryostat assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Water Chiller Fab. & Inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryostat Cool & Vib. Test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pay. Install. Tooles Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pay. Install. Tooles Fab. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryo-Payload Inst. to EXC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cro-Payload Inst. to EYC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cro-Payload Inst. to IXC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cro-Payload Inst. to IYC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EXC Pay. Cool Down |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EYC Pay. Cool Down |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IXC Pay. Cool Down |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IYC Pay. Cool Down |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pendulum
Platform Design & Fab.
Sapphire Suspension
Payload Assembly
Cryostat
Installation
Cool Down
Depend on
Clean Both
Depend on
Mirror Delivery

## Slide 14
KAGRA Cryogenics Group
Toshikazu SUZUKI
Chief
KEK, Prof.
Nobuhiro KIMURA
Cryostat sub-chief
KEK, Assoc. Prof.
Kazuhiro YAMAMOTO
Cryo-Payload sub-chief
ICRR, Assist. Prof.
Takayuki TOMARU
Cryo-Payload
KEK, Assoc. Prof.
Tatsuya KUME
Surveying, Alignment
KEK, Assoc. Prof.
Rahul KUMAR
Simulation, Payload
KEK, PD
Yusuke SAKAKIBARA
Cryostat, Scattering
ICRR, Grad. Student
Dan CHEN
Cryo-Payload, Q
ICRR, Grad. Student
Ayako HAGIWARA
CAD
KEK, Technical Staff
Shinichi TERASHIMA
Machining
KEK, Technical Staff
Iwao MURAKAMI
Welding, Assembly
KEK, Technical Staff
Hiroki TANAKA
Cryo-Payload, Q
ICRR, Grad. Student
Takahiro MIYAMOTO
Cryo-Payload
ICRR, Grad. Student
Suguru TAKADA
Cryogenics
NIFS, Assist. Prof.
@ Feb. 2015

## Slide 15
KAGRA Cryogenics Group
Toshikazu SUZUKI
KEK, Prof.
Nobuhiro KIMURA
Cryostat sub-chief
KEK, Assoc. Prof.
Kazuhiro YAMAMOTO
Cryo-Payload sub-chief
ICRR, Assist. Prof.
Takayuki TOMARU
Chief, Cryo-Payload
KEK, Assoc. Prof.
Rahul KUMAR
Simulation, Payload
KEK, PD
Ayako HAGIWARA
CAD
KEK, Technical Staff
Shinichi TERASHIMA
Machining
KEK, Technical Staff
Hiroki TANAKA
Cryo-Payload, Q
ICRR, Grad. Student
Takahiro MIYAMOTO
Cryo-Payload
ICRR, Grad. Student
Suguru TAKADA
Cryogenics
NIFS, Assist. Prof.
@ Apr. 2016
Kieran Craig
Cryogenic Payload
ICRR, PD
Haino-san & Vocca-san
joined
-4 + 3 = -1 people
Need some of
• Man power
(not helper but expert)
• Money
• Time

## Slide 16
Back Up

## Slide 17
17
Schedule 1
By March 2016 : Development of jigs for HCB
By May 2016 : Development of indium bonding
By July of 2016 : Procurement
of all sapphire parts
By August 2016 : Assembly and test of prototype
September 2016 : Hydroxide Catalysis
Bonding (ETM) is applied.
By March 2017 : Assembly and test
of sapphire suspension (ETM)

## Slide 18
18
Schedule2
April 2017 : Hydroxide Catalysis
Bonding (ITM) is applied.
By June 2017 : Assembly and test
of sapphire suspension (ITM)
August 2017 - February 2018 : Installation of cryogenic payloads
(2 months for one payload)
September 2017 – August 2018 : Cooling