Schedule Tracking Scheme
2016/8/25
Yoichi Aso (SEO)
on behalf of T. Uchiyama

---
Problems so far
No schedule chart is made
People do not keep the schedule even if a chart exists
Schedule charts are not updated
SEO did not track the progress status
What we want
SEO knows what tasks are currently going on (e.g. design OO or
test XX).
SEO knows the progress of each task
SEO knows the expected finish date of each task
SEO knows who is responsible for each task
SEO knows the cost estimate of each task
Granularity of the tasks tracked by SEO is weeks to a month

---
What is necessary
Each subsystem submits a schedule chart to SEO
The chart should contain necessary information
who is responsible for what, cost, etc.
The schedule chart should be updated regularly
Progress of each task should be reported at the same time
An easy way to share the above information
All of the above have been tried in the past
Why did we fail ?
SEO did not ask the status of the schedule to subsystems.
We had problems with MS Project (now solved)

---
What shall we do now ?
Initialization
Each chief submits a schedule chart to SEO
Deadline 7/15
Format: MS Project
Uploaded to KAGRA Project Server
Granularity of the tasks should be a few weeks
SEO(T. Uchiyama) will combine the submitted charts to an unified KAGRA wide
schedule chart.
Regular schedule tracking
Each chief updates the schedule chart by Wednesday of the week before
each chief meeting
Update the progress percentage of each task
SEO(T. Uchiyama) checks for delayed tasks and ask the chiefs for more
explanation.
If necessary PM will put the issue on the agenda of the following chief meeting
SEO(T. Uchiyama) creates an updated project wide schedule chart