## Slide 1
Installation of VIS hardware
Yoichi Aso @ Extended Chief Meeting 2018/5/28

## Slide 2
Summary of the current status: Type-A
ETMY: installed
  F1 – F3 GAS are stuck
    F3 will be released by adjusting the weight at BF in Sept.
    F1, F2 will be repaired after O3
  Accelerometers on PI are noisy: will be replaced in Sept.
ETMX: installed
ITMX: Hardware installation completed (4+ months)
  Connect to DGS in mid June
  Control test in July
ITMY: Installation started
  To be finished at the end of August (in 3+ months)

## Slide 3
Summary of the current status: Type-B
BS: installed
  Control tuning still necessary
SR2: assembled up to SF
  Waiting for the top blades
SR3: assembled up to BF
  Assembly up to SF will finish in this week
SRM: start assembly from August 1st
  Expected to finish the mechanical installation by Oct. 4th
Top filter blade status
12 blades will be delivered in this week
Remaining ones in the next week ?

## Slide 4
Man power
Type-A
Takahashi (leader), Okutomi, Sato, Ishizaki
A Mirapro worker (until the end of Sept. ?)
Type-B
Mark (leader), Fabian, Hirata, Enzo
Kozu (ICRR), Yoshioka (Toyama)
Ohishi (until Sept. ?)
Fujii ?
Type-Bp
Shoda (leader)
Miyo (ICRR), Hashimoto (Hosei), Arai (ICRR)
Kasuya (TITECH), Yoshida (Summer student)
OMMT: Ohishi, Watchdog: Tanaka

## Slide 5: VIS installation schedule
2018 |  |  |  |  |  |  |  | 
4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SR3 bottom
SRM
SR2/SR3 top
Type-B
ITMX
ITMY
ETMY Repair
Type-A
予備期間
X-arm test
DRMI
/Y-arm
ETMY control/pumping

## Slide 6: VIS man power
Type-A
Takahashi
Sato
Shimizu (Mirapro): 5/29 – 9/30
Lucia Torozzo: 7/1 -
Ishizaki: Mitaka
Type-B
Mark
Enzo
Hirata
Kozu
Fabian: 7/15 –
Fujii
Tanioka
VIS control
Shoda
Okutomi: from August
Arai