## Slide 1: Current status of OMMT/OSTM
Naoko Ohishi Nov. 26th 2018
OMMT1
OMMT2
OSTM

## Slide 2: Type-C works in 2018:
Apr: Design
May: MCo visual inspection
Jun-Jul: IMMT1/2 IM screws changed
Aug: Ordered mechanical parts (OMMT)
Sep: Ordered remaining parts (OSTM)
From the mid Oct: started work in the tunnel
  2 weeks for OSEM test with help from four B4 students of Toyama University; Kaihotsu-san, Mori-san, Ito-san and Kuromiya-san (2 days each) and Mark-san, Yamamoto-san, Kokeyama-san about digital system and great help from K. Arai-san (3days).

## Slide 3: tested 17 OSEMs
Results:
http://klog.icrr.u-tokyo.ac.jp/osl/uploads/6828_20181102130917_characteristicsofosem.pdf
http://klog.icrr.u-tokyo.ac.jp/osl/?r=7074

## Slide 4
In addition, Ito-san and Shimizu-san(Mirapro)helped cabling

## Slide 5: From 5th to 14th Nov : Assembled mechanical parts
Horio-san(B4) and Tsuda-san(M1) came from Tohoku-gakuin university.
They assembled mechanical parts and set tungsten wires.
We found some problems. Samejima-san(MESCO) repaired them really quickly but we still needed to reproduce two kind of mechanical parts to finish assembly.

## Slide 6: In parallel, glued standoff and magnets on OMMT1/2 mirrors.

## Slide 7: Last week(19th-22th) OMMT1 assembled
All the parts came on Monday.
Ito-san(21, 22th) and Kaihotsu-san(22 and 23th) came to help.
R. Takahashi-san also joined from Wed(30min) and Thu.
Miyakawa-san helped to make OSTM model.
So we completed assembly and took transfer function.

## Slide 8: OMMT1 transfer function

## Slide 9: This week:
Mori-san (Tue, Wed), and Kuromiya-san(Thu, Fri) will come.
Tsuda-san, and Horio-san will work on Tue, Wed and Thu.
I hope that R. Takahashi-san also joins us.
Remaining works:
OSTM glueing
OMMT2, and OSTM assembly (half a day for each)
Transfer Function measurement…
Lock, install and release in the vacuum chamber.

## Slide 10: Next week
Peel first contact away and finish.
Status Summary
OMMT1 transfer function measured outside the vacuum.
Check TF in Tue and Install in Wed.
OMMT2 will be assembled(Tue; Tsuda-san, Horio-san) and will measure TF.
Installation (Thu).
OSTM glueing(Ohishi), set in suspension in Wed(R. Takahashi-san), measure TF on Thu(Kuromimya-san)
Installation (Fri).