## Slide 1: For cooling down; the risk and process
N. KIMURA/ICRR
On behalf of KAGRA Cryogenics Group

## Slide 2
Contents
  What are ”the Risk of Cryogenic”?
  Proposal for Cooling Process of the Mirrors
  Toward O4

## Slide 3: What are ”the Risk of Cryogenic”?
The biggest risk of mirror cooling are frost and dew on the surface of mirror.
TM oplev light source side
TM oplev QPD side
The frost or dew is caused by mostly vacuum leak, residual gas and outgassing from super insulations.

## Slide 4
IYC
EXC
Frost
Out gas analysis by Mass-Spectrum Meter
Frost Issue at cryogenic Temp.
H2O
N2
O2
H
O
Tinny vacuum leakage can cause frosting
on mirrors
Commissioning team found small finesse of Fabry-
Perot cavity in Y arm.

## Slide 5: Example @ EXC
9/1 9:10~ EXC cryocooler stop
Release of the adsorbed gas
Vacuum pressure during
cryogenic operation：5 x 10-4 Pa
What are ”the Risk of Cryogenic”?
Second risk of the cooling is suddenly
stop due to the malfunction of cryocooler.

## Slide 6: Constitution of the KAGRA Cryogenics
Four 4K cryocooler units per one cryostat
Baffles against wide scattering is cooled via 8K shield.
Main Beam
Cooling 8K shield
Cooling
Cryo-Payload
Duct Shield
400kW
4W?
~1W
Cryostat
80K shield
8K shield
two units
80K PTC with
Vibration reduction
4K PTC with
Vibration reduction
two units
2 units for cool cryo-payload
2 units cool for 8K shield
4 units cool for 80K shield
Low vibration in U. H. Vacuum
Stop propagation of 300K radiation
Prevent heating by scattered beam
300K
Radiation
Baffles
Duct shield is not effective for N2 as trap.
It is effective for H2O.
8K radiation shield is effective
for N2 and other residual gas as trap.

## Slide 7: 1x10^-3 Pa → ~-220 ℃（~53 K）
Solid
Super Critical
Liquid
Gas
Boiling point
Triple point
Phase diagram of nitrogen
Pressure (MPa-abs)
Temperature (℃)

## Slide 8: Proposal for Cooling Process of the Mirrors
Cooling sequence prevent frosting on the mirror
  Vacuum pumping for around 2.5 week for inside pressure < 1x10-4 Pa
  Start duct shield cooling. It takes 2 weeks.
  for inside pressure < 1x10-5 Pa
  TM will be ~240K
  Start 8 K inner radiation shield of the cryostat.
  cooler #1, 3 ON. It takes 2 weeks. ・Inner radiation shield will be ~100K ・ TM will be ~100-90 K for 4 weeks
  ・ inside pressure < 5 x 10-6 Pa
  Start TM cooling：cooler #2, 4 ON
  1 week for TM=100K, and more 1 week for 20K
Total 12.5 weeks for cooling TM

## Slide 9: The present measures to the end of the O3
schedule * The “thermal shield ducts”, presently being cooled, should continuously be kept as they are without EXC, for avoiding interference of commissioning procedure.
But in order to do so, it is to be noticed that we have to have a risk of failure in rotary valves used for the refrigerators. * The “cryostat” in the IXC and IYC can first be cooled down, if the commissioning/noise hunting is proceeded: the ITM’s may be reached to the temperature of around 100K when joining O3.

## Slide 10: Toward O4
  To reduce possibility of frosty or dew on the mirror,
  It needs to repair vacuum leak points.
  We found vacuum leak points level of ~10-8 Pam3/s at EXC and EYC.
  Add cryogenic residual gas trap to both side of the cryostat.
  Replace duct shield cryocooler step by step.
  Maintenance cycle of duct shield cryocooler is very short time.
  It is almost 3,000 hours.

## Slide 11
Leak point @ EYC
~10^-8~9 Pa･m^3/s
Leak point @ EXC & EYC
~10^-8~9 Pa･m^3/s
Leak point @ IYC
~10^-8~9 Pa･m^3/s
Examples of the leak point

## Slide 12: Appendix

## Slide 13
Temperature (K)
Vapor pressure (Pa)

## Slide 14: 2018.03.17_中央ダクトHe試験結果 東大：内山先生、MPC：中村、山田、由井 単位：Pa・m^3/s 機種：ライボルト 文字色：締結部/黒、締結部-08/赤 排気系：緑 容器のフランジ類：橙
3.1E-09
6.1E-09
Y
X
1.5E-08
5.1E-09
6.0E-09
5.9-09
PR3
PR2
BS
PRM
IMM
IFI
3.0E-09
3
11
2
5.6E-09
6
5.0E-09
10
6.0E-09
5.7-09
7.5-09
1.0E-08
7.7E-09
7.6E-09
3.0E-09
13
3.1E-09
7.5E-09
1.0E-08
7.5-09
7.5-09
7.5-09
7.5-09
4.9-09
5.8-09
5.6-09
5.0-09
6.1-09
6.6-09

## Slide 16: The present measures to the end of the O3
＜Watch Items＞ (1) Monitoring of temperature and gradient of dT/dt
(2) Vacuum Pressure (3) Monitoring of operation of duct shield
(4) Frost of mirror by Oplev or stifness
(5) Temperature distribution, and others